FIELD REPORT

SURVEY OF MASSACHUSETTS WELFARE LEAVERS

Background

The following is a description of the data collection on the Massachusetts Welfare Leavers Study conducted 1999-2000 by the Center for Survey Research at the University of Massachusetts Boston under contract with the Massachusetts Department of Transitional Assistance.  Funding for the project was provided by  ASPE, the Office of the Assistant Secretary for Planning and Evaluation of the U.S. Department of Health and Human Services.

Mary Ellen Colten was the Study Director from CSR.  Carol Cosenza served as Project Manager.  Carrie Spearin was Assistant Study Director.

The study tracked two groups of recipients who left or were scheduled to leave the Temporary Assistance to Needy Families (TANF) program between  December, 1998 and February, 1999.  One group was scheduled to leave the rolls during that period because they reached Massachusetts’s two year time limit and the other left during the same period for all other reasons.  Interviews were conducted both in person and on the telephone.  The survey explored how families are doing after leaving welfare with respect to employment, employment stability, income, child support, living arrangements, food security, child care, child health and well being, health care, and transportation. Questions were included about barriers to employment and economic self sufficiency, such as domestic violence, family responsibilities, health and mental health problems.

Questionnaire Development

Initial Draft

The initial draft was developed by CSR, in collaboration with DTA.  Choice of  content and final decisions about question wording were the responsibility of DTA.  Whenever possible, an attempt was made to replicate items from other studies, especially from other current ASPE-funded studies of welfare outcomes.

Pretesting

The questionnaire development process included at total of 18 interviews in two phases.  The first pretest of 12 interviews took place from August 4-12, 1999.  Three experienced field interviewers who were well briefed on the question objectives conducted the interviews.  A debriefing was held to review question problems and the questionnaire was revised.  The second pretest of six interviews, conducted in the last week of August, was followed by another debriefing and set of revisions.  All pretest interviews were taped and behavior coded.  The pretest sample provided by DTA  was comprised of respondents who had been off assistance for approximately two months at the time of the interview.  Pretest respondents were paid for their participation.

Final Questionnaire

The final questionnaire was translated into Spanish.  The English and Spanish versions of the questionnaire are in Appendix A of this report.

Sampling

The universe of cases considered for sample selection consisted of both TAFDC closings and those scheduled for closing due to time limits in the DTA files for the months of December 1998 through February 1999.  Closings were divided into three separate groups:   1) time limit closings, 2)  closings for reasons other than time limit, and 3)  cases which reached their time limit but who requested an extension.  For sampling purposes, groups 1 and 3 were considered together as time limit cases, and group 2 was the non-time limit cases.  Cases had to remain closed for at least two months to be considered in the sample universe.  In addition, cases which were scheduled to close from December 1998 through February 1999, but who had requested an extension, were still considered part of the sample universe if they closed by April 30, 1999.  (This date was chosen so that these cases would be not receiving benefits for an appropriate amount of time before interviewing began in the Fall of 1999.)  Finally, cases with a closing date prior to December 15, 1998 were eliminated from the sample because these cases actually received their last benefits in November 1998.  Table 1 summarizes the sample universe as computed by DTA.

Table 1:  Sample Universe of TAFDC Closings as Computed by DTA

|  | Universe |  |
| --- | --- | --- |
| Time Limit Cases: |  |  |
| Time Limits: December 1998 | 1285 |  |
| January 1999 | 251 |  |
| February 1999 | 281 |  |
| Extension Requests: December 1998 | 1792 |  |
| January 1999 | 268 |  |
| February 1999 | 208 |  |
| Total Time Limit: | 4085 |  |
| Non-Time Limit Cases: |  |  |
| December 1998 | 2374 |  |
| January 1999 | 2028 |  |
| February 1999 | 1993 |  |
| Total Non-Time Limit: | 6395 |  |
| Grand Total of All Cases: | 10480 |  |

From the universe of cases, DTA randomly selected 1066 non-time limit cases and 1634 time limit cases.  Those cases were delivered to CSR for further examination and subsampling.   CSR examined  the 2700 cases delivered, and further eliminated cases for any one of the following reasons:

- The case had left Massachusetts.

- The case was a duplicate of another in the file as determined by social security number.

- From information about closing dates on the files, the exact dates indicated that the case did not actually close within the sample time frame.

- From information contained about opening and closing dates on the file, the case did not remain closed for at least two months.

The first two reasons for elimination are obvious as we were not pursuing cases out of state, and a case could only be selected once for the sample.  When duplicate cases were found, one was randomly selected to remain in the sample.  The last two reasons simply indicate that the case had some confusing characteristics which placed them in the original sample universe, but upon closer inspection, they should not have been there.  Table 2 indicates the number of cases eliminated by CSR from the sample for the various reasons.

In addition to CSR’s elimination of cases, DTA also eliminated an additional 53 cases from the time limit group as they determined them to not be eligible for the sample.  This left the time limit group with 1378 eligible sample cases.

Table 2:  Results of CSR’s Examination of the DTA Sample

|  | Non-Time Limit Cases |  | Time Limit Cases |  |
| --- | --- | --- | --- | --- |
|  | 1066 | Delivered by DTA | 1634 |  |
|  | 3 | Found to be Out of State | 0 |  |
|  | 52 | Duplicate Social Security Number | 46 |  |
|  | 0 | Closed Prior to December 15, 1998 | 76 |  |
|  | 0 | Extension Requests not Closed by April 30, 1999 | 67 |  |
|  | 0 | Not closed for 2 months | 14 |  |
|  | 1011 | Remaining Sample | 1431 |  |

From these cases, CSR randomly selected 620 time limit cases and 310 non-time limit cases to form the sample for this study.  All of these cases were attempted to be contacted for an interview.  From the information given, the probabilities of selection for each sample group can be computed as follows:

Non-Time Limit Cases:  (1066/6395)(310/1011)=.0511

Time Limit Cases:  (1634/4085)(620/1378)=.1800

Based upon these probabilities of selection, the base weights, or inverses of the probabilities of selection, are 19.5647 for non-time limit cases and 5.6129 for time limit cases.  Within each of these two groups, the sample is a simple random sample.  As such, for within group analyses, these cases need not be weighted to produce estimated percentages, regression, coefficients, and other such statistics.  The weights would only be required if estimated population totals were desired.

If the two sample groups are to be combined for statistical analyses, then they must be weighted to reflect the different probabilities of selection.  The base weights could be used, or the base weights multiplied by the inverses of the response rates for each group could be used as a weight that takes differential nonresponse into account.

Field Procedures

Interviewers were briefed by Mary Ellen Colten and Carol Cosenza on September 16, 1999.  Fifteen interviewers worked on the project.  Dorothy Cerankowski, the Field Manager, also interviewed on the project.  Interviewing was done over a six and one half month period with the last interview completed on April 5, 2000.

An advance letter, along with a fact sheet and a postage paid card asking for the respondent’s phone number was mailed to all sample members at the address listed in the DTA’s records.  These materials were in both Spanish and English.  All study materials can be found in Appendix B.

Interviewers began by attempting to interview respondents by telephone before making field visits. Of a total of 670 interviews, 577 were completed on the telephone and 93 were completed in person.  However, fully a third (227) of the completed telephone interviews could not be completed without some field activity.  In addition to the 93 in-person interviews, 134 of the telephone interviews  required field visits for tracking, obtaining a telephone number,  or for enlisting cooperation, even though the interview was ultimately conducted on the telephone.

Interviews averaged 57 minutes in length:  56 minutes for telephone interviews; 60 for in person.  Interviews averaged 3.5 hours of interviewer time per completed interview.

All respondents were paid $50 for their participation.  Respondents were asked if they had no checking account and, if not, if they had a way to cash a check that would not cost money.  Respondents who had neither  were given the option of receiving their payment in the form of a money order, rather than cash.  Money orders were requested by 207 (30.9%) of the respondents.

Fifty-nine (8.8%) of the interviews were conducted in Spanish.  Twenty interviews were conducted in other languages (Korean, Laotian, Vietnamese, Russian, and Portuguese), using an English-speaking member of the respondent’s household as an interpreter.   The interpreter-assisted interviews were conducted with truncated versions of the questionnaire.   In those cases, Interviewers were provided with a set of priority questions (e.g., employment status, income, food, security, household composition) to be covered first, with instructions to continue with additional questions dependent upon time and stamina of the respondent and the interpreter.

The primary difficulty in this study was locating respondents.  Tracking efforts included directory assistance, post office forwarding information, field visits to last known address and questioning neighbors when feasible and appropriate within confines of confidentiality, information from Massachusetts Department of Motor Vehicles, rechecks of DTA’s records, including address of record for food stamp receipt.  We were unable to obtain any tracking information from other state agencies.

As part of the tracking effort and to increase efficiency, FedEx packages, including a letter, a factsheet, and colorful flyer,  were sent on November 8, 1999 to 125 sample members whom we had been unable to reach by telephone and whose initial mailing had not been returned by the post office as undeliverable.  Essentially, FedEx provided a tracking service.  If they were unable to locate the respondent at the address,  we could save the effort and expense of a field visit to the address.  We hoped that respondents who were at the address and did receive a FedEX would call us on our 800 number or send us the location postcard after receiving the FedEx package, but very few FedEx recipients actually contacted us.   We did ultimately interviews with 78 of the FedEx recipients.

Field Outcomes

The results of the data collection for the total sample are displayed in Table 3.  Breakdowns by time limit/non-time limit are shown in Tables 4 and 5.

A total of 670 interviews were completed: 460 with time limit cases and 210 with non-time limit cases.  The response rate was 75.2% for the study overall.  There was not a significant difference in response rate between the time-limits and non-time limits groups: the final response rates for the groups were 75.5% and 74.4% respectively.

Eligibility:  Respondents were deemed ineligible if they had moved out of state, were determined to be deceased, or if they insisted that they had never received TAFDC.   Of the initial sample, 3.9% (25) had moved out-of-state and were therefore ineligible according to criteria established for the study.  Not surprisingly, the out-of-state cases were disproportionately non-time limit cases.  Moving was likely the reason for leaving the rolls.  It is likely that many of the sample members we were unable to contact had also left the state, but we were unable to establish that with certainty nor to have a informed basis for making a estimate, so they all “unable to locate” cases are considered to be eligible in the response rate calculations.

One person was deceased.  Two others were considered ineligible because they were adamant that they had never received TAFDC.

Non-Interviews:    Refusals were not a major factor in non-response in this study; only one quarter of non-interviews were due to refusals.  Refusal conversions were attempted in 30 cases, 7 of which (23%) were successful.

Despite extensive effort, we were unable to locate 84 respondents (9.4%).  In addition to sample members whom we were unable to locate, there are 74 (8.3%) whom we located, but were unable to interview despite repeated attempts.  (These cases are coded as “limits” in Tables 3-5.)  There are also nine sample members about whose whereabouts we are uncertain, for whom we believe we had the correct address but were unable to verify our suspicion,  thus are in the “other” category since they could not be categorized as either “not able to locate” or as located.

Data Entry, Coding, and File Creation

Trained coders on CSR’s staff used a preprogrammed data entry system for coding and entering the interview data.  All data entry was 100% verified by a second coder.   After data were extracted from the coding system, marginal frequency distributions and contingencies were reviewed and inconsistencies reconciled when possible.   A codebook and SPSS data file were produced.  The codebook is in Appendix C.  The marginal distributions for time limits and non-time limits cases are in Appendixes D and E.

TABLE 3: FIELD RESULTS TOTAL SAMPLE

| Total Sample |  | 930 |
| --- | --- | --- |
| Not Eligible |  | 39 |
| Out of State | 36 |  |
| Claimed no TAFDC | 2 |  |
| Deceased | 1 |  |
| Total Eligible Sample |  | 891 |
| Non-Interviews |  | 221 |
| Refusals | 54 |  |
| Limit | 74 |  |
| Not Able to Trace | 84 |  |
| Other | 9 |  |
| Interviews |  | 670 |
| Phone | 577 |  |
| Field | 93 |  |
| RESPONSE RATE |  | 75.2% |

TABLE 4:  FIELD RESULTS TIME LIMITS

| Total Sample |  | 620 |
| --- | --- | --- |
| Not Eligible |  | 11 |
| Out of State | 11 |  |
| Claimed no TAFDC | 0 |  |
| Deceased | 0 |  |
| Total Eligible Sample |  | 609 |
| Non Interviews |  | 149 |
| Refusals | 40 |  |
| Limit | 54 |  |
| Not Able to Trace | 48 |  |
| Other | 7 |  |
| Interviews |  | 460 |
| Phone | 390 |  |
| Field | 70 |  |
| RESPONSE RATE |  | 75.5% |

TABLE 5:  FIELD RESULTS NON-TIME LIMITS

| Total Sample |  | 310 |
| --- | --- | --- |
| Not Eligible |  | 28 |
| Out of State | 25 |  |
| Claimed no TAFDC | 2 |  |
| Deceased | 1 |  |
| Total Eligible Sample |  | 282 |
| Non-Interviews |  | 72 |
| Refusals | 14 |  |
| Limit | 20 |  |
| Not Able to Trace | 36 |  |
| Other | 2 |  |
| Interviews |  | 210 |
| Phone | 187 |  |
| Field | 23 |  |
| RESPONSE RATE |  | 74.4% |